Canada-Alberta
Enhanced Language Training for Skilled Immigrants

| Cover Page |  |
| --- | --- |
| Applying organization (Operating Name) Robertson College |  |
| Legal name if different than above Midwestern School of Business and Technology |  |
| Act registered or incorporated under (i.e. Societies Act, Companies Act, etc.): Companies Act |  |
| Incorporation Date: November 1997 Registration Number: 3738168 |  |
| Phone number and fax number 403 – 920-0070 ext 23 /fax 403 – 263-8176 |  |
| E-mail address mmacminn@robertsoncollege.com |  |
| Project Title Pharmacy Preparation for Foreign Trained Pharmacists |  |
| Is this a Delivery or a Development project? Briefly describe the project. Delivery – January 2007 to December 2008 |  |
| CLB Entry ___CLB 7/8_____________ CLB Exit __CLB 8/9__________ |  |
| Total number of beneficiaries 20 to 30 | Number who are Canadian Citizens 5 |
| Total Cost $437,578.00 |  |
| Total Amount Requested $424,828.00 |  |

September 1, 2006

## Dear Review Panel:

## Robertson College would like to take this opportunity to submit the accompanying proposal to apply for funds from Canada – Alberta’s Enhanced Language Training for Skilled Immigrants Program. These potential funds would make it possible for Robertson College to deliver a Pharmacy Preparation for Foreign Trained Pharmacists Program that is currently under development. I would like to provide for your consideration some background information about Robertson College and the proposed delivery project.  The full proposal will follow this letter of introduction.

Robertson College – Background:

Robertson College is one of Canada’s oldest private schools, established in 1911 in Edmonton and Saskatoon. There are currently three campuses in Canada – Winnipeg, Manitoba (main campus), Brandon Manitoba and Calgary, Alberta.

A number of vocational/ESL training programs have run in China and the Philippines in addition to the ESL and vocation skills training initiatives in Canada.

Our mission is to provide quality, practical training programs that will prepare our learners with the essential skills that will enable them to secure rewarding, fulfilling careers. Our mandate is to successfully graduate learners as opposed to enrolling learners.

Robertson College Calgary received recent approval for tuition based funded ESL programs under Skills Development Program. Three employment and occupation specific programs will be offered starting October 2006 to immigrants/ESL learners who have finished LINC training, have a minimum CLB 4/5 and are looking for additional language training that will lead to employment or further education that will lead to employment:

- ESENCE: English Skills for Employment, Networking and Career Exploration

- Maple Health Care Aide – An ESL Integrated Skills Training program that will prepare learners to meet the entrance requirements to enroll and succeed in the Government of Alberta Health Care Aide Certificate program.

- Maple Pharmacy Technician Program - An ESL Integrated Skills Training program that will prepare learners to meet the entrance requirements to enroll and succeed in the Pharmacy Technician Diploma program that is recognized by the Pharmacy Technician Certification Board of Alberta.

Program Introduction:

Robertson College received a program development grant from AHRE in April 2006 in order to develop a Pharmacy Preparation for Foreign Trained Professionals program. We are half way through our project and expect to complete the program development by January 2007 at which time we would like to pilot the delivery of the content and model that we have researched and developed.

The intent of the program is to prepare foreign trained pharmacists who are not working in their profession to acquire the skills, knowledge, language and cultural competency that will lead to successful results on the qualifying exams and practicum requirements leading to licensing as a Pharmacist in Alberta.

The Pharmacy Preparation for Foreign Trained Professionals program is a technical and communication skills preparation program into which language and cultural competencies will be integrated. This delivery model will bridge the language and cultural knowledge gaps that stand in the way of foreign trained pharmacists’ ability to successfully complete the assessment and evaluating process needed to obtain a license as a Pharmacist in Alberta.

A preceptor manual had been part of the development project plan however we have learned that the Bredin Institute in Edmonton is working on a Preceptor Manual and we don’t wish to duplicate what is already being developed by a very reputable school. We have therefore chosen to focus on the OSCE prep that will focus on the development of skills that will support pharmacists in developing patient care competencies that are vital to their success in the OSCE exams.

Robertson College Calgary is well known in the Pharmacy Community as a result of the Pharmacy Technician Program that has been running for two years. The Pharmacy Technician program is recognized by the Pharmacy Technician Certification Board of Alberta which means that graduates are eligible for certification and can work in both the retail sector as well as the hospital sector. Robertson College has an established Pharmacy Technician advisory committee made up of representatives from the pharmacy community who are supportive of Robertson College moving forward to offer a Pharmacy Preparation for Foreign Trained Professionals program.

Robertson College is equipped with many of the basic technical resources that will be required in delivering a Pharmacy Preparation program. In addition to technical material, we have a Pharmacy Lab complete with two Sterile Hoods, pharmacy software, medication preparation stations and a comprehensive inventory of pharmaceuticals. The lab and materials will be instrumental in the application of the program curriculum.

We have an advisory committee consisting of members of the Pharmacy Community. Three of the five members have gone through the qualifying process and the other two represent large companies that employ pharmacists and support our program.

I look forward to hearing from you with the results of your review.

Sincerely,

Maria MacMinn

Director, Robertson College Calgary

600 900 6 Ave. SW

Calgary, Alberta

T2P 3K2

Table of Contents

Executive Summary	5

Client Eligibility:	5

Numbers of Learners:	5

CLB Entry And Exit Levels:	5

Labour Market Information:	5

Program Model and Implementation	7

Program Delivery Model	7

Resources That Will Be Used In the Program	8

Project Time Lines	9

Description of Intake Process	9

Integrated Skills Training Model	9

Staffing Model	10

Objectives and Summary of Proposed Activities	10

Expected outcomes	10

Project Work plan	11

Project Costs	18

Total Project Budget	Error! Bookmark not defined.

Apprendix # 1 - Practicum Sites and Employers	20

Appendix#2 - Sample Curriculum Planning Documents	22

Appendix # 3 - Project Staff Job Descriptions	25

Roles and Responsibilities of Staff Involved In the Project	25

Appendix # 4 – Timelines Spreadsheet	27

Appendix # 5 - Background Information	28

Appendix #6 – Letter of Support	30

Appendix # 7 - Robertson College Organizational Chart	31

Appendix #8- Certificate of Incorporation	32

Appendix #9 – Most Recent Financial Statement	33

Appendix #10 – Insurance Certificate	34

Appendix #11 - Declaration	35

Executive Summary

## Client Eligibility:

The Pharmacy Preparation for Foreign Trained Pharmacists Program will be targeting the following individuals:

Foreign trained Pharmacists:

- whose credentials are not recognized in Canada by educational institutes, employers and Alberta College of Pharmacists, PEBC and NAPRA

- whose English language skills are not adequate enough to secure employment in their field of training

- who would benefit from employability and essential skills training with a focus on cultural competency preparation for the OSCE exam

- who meet our basic English language requirements:

  - Minimum of CLB 7 in reading/writing/listening and speaking

## Numbers of Learners:

The project anticipates recruiting and delivering the program to:

- 20 to 30 foreign trained Pharmacists

- no more than 5 out of the 20 to 40 will be Canadian citizens

## CLB Entry And Exit Levels:

- CLB 7/8 entry

- Exit CLB 8/9

## Labour Market Information:

According to Alberta Labour Market Outlook 2019 – 23 report that ranks the top 10 Occupations experiencing labour shortages, Pharmacists are ranked third with a 7.6% estimated job vacancy rate. This percentage represents the job vacancy rate of positions that have been unfilled for 4 months or more.

Federal and provincial governments are implementing strategies to reduce the labour market shortage by turning to immigration as a serious labour market solution. The federal government last year announced an initiative and funding allocation responding to the need to reduce the wait times for assessment of foreign trained professionals’ credentials. The following is taken directly from a News Release by Health Canada in April 2005:

“At the First Ministers Meeting in September 2004, the Government of Canada and the provinces and territories agreed to accelerate and expand the assessment and integration of internationally trained health care professionals. The 2005 federal budget provided $75 million over five years to support this objective, which will help address shortages of health care professionals and assist efforts to reduce wait times.”

Although the government has changed since this First Ministers Meeting, the current government is committed to the goals of this original initiative.

These two factors: labour market shortage and government response to make accreditation more accessible to foreign trained professionals, lead us to believe that there will be a high demand from foreign trained Pharmacists in Alberta to access the accreditation process. Subsequently there will be a need to support foreign trained Pharmacists to be successful in the accreditation process with Pharmacy Preparation courses that not only address skills training but also involve language and cultural support.

Program Model and Implementation

## Program Delivery Model

We will offer a delivery model that will accommodate participants that may need to work as well as study. As a result, we will be piloting a model that will promote an advocacy approach on an individual and workshop basis. After feed back from the advisory committee and the ACP education group that also piloted a delivery project, it became very clear that:

- Foreign pharmacists were asking for support and guidance from the beginning of the process following through to the practicum level.

- The actual qualifying exams are not as much an issue as the support that they need throughout the process.

- They want to go through the process of applying and preparing with the support of others who are going through the same process. Support, guidance, advocacy and motivation were more important than the actual technical support.

- All indicated that language and technical support for the OSCE exam was more important than the technical prep for the Qualifying exams which they had the knowledge for but needed additional study and language strategies for.

- The Pharmaceutical Care model of the OSCE exam was the most difficult for foreign trained pharmacists to develop competency in. This is the area that is in the most demand for training.

As a result of and in response to this feedback we will be piloting the delivery of the program in the following manner:

Program Delivery:

- Weekly, part time ongoing workshops and individual counselling sessions.

- Orientation and Resource Workshops (four 2 hour sessions to help individual with start up process)

- The orientation component will explain to and assist foreign trained professionals with the two step evaluation process. Participants will be assisted with the process of document evaluation that is a prerequisite to writing the three exams.

- Process Counselling ( Individual counselling to help individuals throughout the application process)

- Technical Review Exam Preparation for the Qualifying Exam Part I (MCQ) , Evaluating Exam and the QE – II (OSCE – Objective Structured Clinical Exam)  (Weekly 3 hour sessions – 3 month cycle):

- Study and support group to prepare for the multi step evaluation process.

- Technical review workshops

- Language strategies workshops which will include a study guide developed specifically for this program

- Language support for skills and knowledge required to prepare for the two pharmacy exams which will meet Alberta College of Pharmacists and Canadian College of Pharmacist standards.

- Technical Language and cultural competency preparation for the OSCE exam.(The OSCE exam is a practiced based exam in which communication skills are assessed in conjunction with skills and knowledge assessment required in order to be successful in passing the OSCE exam as well as for finding and sustaining employment).

- OSCE Preparation - Language and Cultural competency preparation for the OSCE exam (weekly 3 hour sessions – 3 month cycle)

- This will be based on Case Studies that encompass the Pharmaceutical/Client Care Model competencies outlined in the NAPRA competencies. The Cambridge Calgary model that was developed for foreign trained doctors at the University of Calgary will be used as the model for delivery of this program component.

- Practicum Preparation - Language and cultural competency preparation for practicum ( Weekly 3 hour sessions – prior to practicum placement and during placement – can be up to 1 year long)

- Practicum placements will be drawn from a list of existing Pharmacies that Robertson College has practicum agreements with and additional placements arranged with the support of the Project Advisory Committee. Please refer to Appendix # 1 for a list of Practicum partners.

- Practicum orientation and placement assistance in order to meet the provincial requirements prior to being licensed to practice as a Pharmacist in Alberta.

- Participants will be placed in a 2 week job shadow prior to permanent practicum placement

- Job shadow will be 2 part time shifts a week and one 3 hour weekly class to debrief the experience prior to practicum placement

- Practicum placement will be supplemented by a 3 hour a week workshop to review, discuss and prepare for ongoing practicum requirements

- A practicum competency checklist will be provided to the Preceptor and the learner.

- Follow up of participants:

- Ongoing up to three months after completing the program.  However, a 2 year follow up will also determine if all participants successfully complete the certification process.

Resources That Will Be Used In the Program:

In addition to curriculum material developed for each program component, participants and instructors will have access to the following technical course materials of which the following are only a sampling:

- TIPS – Pharmacy Preparation Material

- Pharmacy: Appleton and Lange’s Quick Review by Berger and Generali, Appleton and Lange

- Review of Pharmacy by Hall and Reiss, Appleton and Lange

- Applied Therapeutics, The Clinical Use of Drugs, ed. by Koda-Kimble and Young, Applied Therapeutics Inc.

- Compendium of Pharmaceuticals and Specialties (CPS), Canadian Pharmacists Association

- Pharmaceutical Calculations, The Pharmacist’s Handbook, by Ansel and Prince, Lippincott Williams and Wilkins

- Pharmacy Management in Canada, ed. by Bachynsky and Segal, Grosvenor House Press Inc. Canadian Pharmacists Association

- Ethical Issues in Pharmacy, Weinstein, Applied Therapeutics, Inc.

- Pharmacy Prep TIPS school who is already offering pharmacy preparation courses will be consulted on pharmacy prep course material

Federal and provincial legislation documents:

- Canada Health Act

- Food and Drugs Act and Regulations

- Controlled Drug and Substances Act (CDSA) and Regulations

- Narcotics Control Regulations

- Benzodiazepines and Other Targeted Substance Regulations

- Marijuana Medical Access Regulations

- Alberta Health and Wellness Blue Cross Formulary

Other:

- NAPRA competency profile for Pharmacists,

- ESL language resources and research sources related to curriculum development of vocational and occupation specific curriculum, CLB documents, Essential Skills documents

Project Time Lines:

- January 2007 to December 2008

The project anticipates offering two classes of 10 to 15 students within a two year period.

- First class – May 2007 to August 2008 – 14 months

- Second Class – September 2007 to October 2008 – 14 months

Description of Intake Process:

We will start early in the project phase to promote and advertise the program. The following will be our outreach and referral contacts and strategies:

- Project Advisory Committee

- Development project Focus Group participants

- Contact ACP pilot project participants

- Advise ACP of project delivery

- Contact immigrant settlement agencies

- Contact Calgary and surrounding Pharmacy community

- Advertise in immigrant/ethnic media

- Contact and promote to ESL schools

Referrals to the program will meet with our Pharmacy Coordinator/Advocate for an admissions interview:

- Determine eligibility and availability to attend the program

- Determine where the individual is in the application process.

The potential participant will also meet with the ESL Instructor to write a CLB test that will:

- Determine entrance language level eligibility

The individual will then be referred to the program components that they will require to progress towards certification.

- Orientation and Resource Workshops

- One on one Process Counselling with Pharmacy Coordinator/Advocate

- Technical Review Preparation for Qualifying,  Evaluating and OSCE exams

- OSCE Preparation Workshops

- Meet with Pharmacy Coordinator/Advocate to arrange a practicum placement

- Practicum preparation workshops prior to and during practicum placement

Integrated Skills Training Model:

The program will be delivered in a synchronous integrated skills delivery model. The majority The Pharmacy Prep program has been developed as original material within the framework of a synchronous model:

- A competency profile has been developed within the Essential Skills/CLB competency comparative framework.

- Language and cultural components are integrated into the technical and communication components.

- Curriculum modules have been developed to interface with the Essential Skills and CLB competencies identified by the competency profile

- Each module/lesson plan will address the paralleled and corresponding essential skills and CLB competencies.(refer to appendix # 2 for sample curriculum planning documents)

- We have used the NAPRA (National Association of Pharmacy Regulatory Authorities) competencies developed as the basis for assessment in the Pharmacy Qualification and Evaluating exams to guide the development of the curriculum.

- Original resources used to prepare for The Qualifying Exam Part I (MCQ), Evaluating exam and The QE – II (OSCE – Objective Structured Clinical Exam) will be supplemented and with language and cultural content.

- Simulated skills and communication scenarios will be set up and practiced in the onsite Pharmacy Lab in preparation for OSCE exam.

- The Pharmacy Lab at Robertson College will be used for hands on practice and computer software practice.

- Supervised job shadowing will be arranged as one strategy in the practicum preparation component of the program.

- Assessment tools will be developed for entrance, ongoing and summative assessment points.  The assessment tools will include indicators that will identify competency benchmarks for each essential skill, language and cultural competency identified in the competency profile.

- Follow-up will be done with each individual participant throughout the program and up to three months after program completion

Staffing Model (refer to Appendix # 3 for Project Staff Job Descriptions):

- Robertson College Director will be the Project Manager for the project and will oversee and manage all aspects of the project.

- Advisory Committee:

  - Continuation of current advisory members and addition of new members that will be able to support the language delivery components

- Hire a Pharmacy Coordinator/Advocate to deliver the Orientation component and to case manage participants through the process counselling component

- The Pharmacy Coordinator will also promote, recruit participants as well as manage the practicum placement component of the program

- Hire two instructors –  A Pharmacy Educator and an ESL Instructor who will work together to deliver the language and cultural competency component of the program

Objectives and Summary of Proposed Activities

Expected outcomes:

- 20 to 30 foreign trained pharmacists will be recruited to attend the program components that relate to their needs for certification preparation

- 70% of the participants will complete the program components and will have successfully completed the qualifying, evaluating and OSCE exams within 2 years of their participation in the program

- Expected exit CLB level – CLB 8/9 for 70% of participants

Project Work plan:

| Time Lines | Activities | Outputs | Outcomes | Indicators |
| --- | --- | --- | --- | --- |
| January 2007 – February 2007 | Organizing and hiring of program personnel | ESL instructor Pharmacy Instructor Participant Advocate/Outreach Project Coordinator | Adequate Professional staff to deliver program | Staff meet the criteria for hiring and are committed to program goals and outcomes |
| January 2007 | Meet with Advisory Committee members | present program plan and recruit new members if necessary | Reestablishes and renews commitment of Advisory Committee members | Current advisory members agree to continue and new members added for additional expertise |
| February 2007 | Train/Orientation of new staff | Establish distribution of responsibilities according to work plan | Project will move forward according to work plan | Staff works as a team and understands individual role to achieve program goals |
| February/March 2007 | Develop Marketing and Promotional Material | Brochures and information package outlining program components and eligibility requirements Program Literature for referral groups Advertising material for Ethnic and Mainstream media | Promotional material and advertising material will reach immigrants who are foreign trained pharmacists or will reach those that can refer potential program participants | Robertson will receive inquiry calls and referrals that meet the admission criteria for the program |
| February 2007 | Create admissions forms and documents for future participants | Pharmacy Coordinator, ESL instructor and Project Manager will create admission forms and tracking documents for participants to fill out and to use at each evaluation stage of the program | We will have documents that we can use to collect and analyze data about the project and for the final report | We will have adequate qualitative and quantitative information for the final report |
| April 2007 | Advisory Committee meeting | Inform advisory committee about staff hired as well as present information brochure/information package to assist in recruitment process | Advisory committee will support and assist in recruitment process | Potential participants will apply for the program with the support of the Pharmacy community |
| Jan 2007 to end of April 2007 | Participant recruitment | Work with Advisory Committee, Immigrant serving agencies, Ethnic organizations, Ethnic and mainstream media, ESL schools, Pharmacy community and associations to promote program to potential participants | We will be able to recruit enough students to start program by May 2007 | We will have a first class of 8 to 10 students to start the first program cycle |
| Mid May 2007 to Mid June 2007 | Start first program cycle with first group of students – Orientation And Resource Workshops (four 2 hour sessions | Pharmacy Coordinator will facilitate the orientation workshops Participants will receive info and guidance on the initial application process. A check list of procedural and process requirements will be given to participants. Participants will receive individual counseling regarding their personal circumstances | Participants will become aware of what they individually need to do to prepare for the first qualifying exam and to be ready for the OSCE and practicum requirements | Participants will have all documents completed and in place to move forward in the application and certification process. Checklist will determine how prepared students are to go on to the next component in the program. |
| Mid June 07 | Initial program evaluation – Orientation and Resource Workshops | An evaluation form will be distributed to all participants An evaluation form will be distributed to Staff. No language assessment will be necessary after the Orientation workshops as this component is informational and individual counseling is related to the process of the application. | Participants and staff will have an opportunity to evaluate the program up to this point | 100% of participants and staff will have filled out the evaluation forms. |
| Mid June to mid September 2007 | Technical Exam Review Component – (first group of students) Workshops, support groups, tutoring to prepare for the Qualifying Exam Part I (MCQ), Evaluation exam and OSCE - . (Weekly 3 hour sessions – 3 month cycle) | Technical Review material will be made available to students. Pharmacy Educator will conduct workshops on, technical content expected on the exams. ESL instructor will conduct study strategies, language strategies workshops to support participants in overcoming the English language obstacles. | Students will be ready to write the MCQ exam. English Reading and writing will have improved enough to be ready for success in the MCQ exam. | Technical mock tests will indicate the participants’ readiness level. CLB/Essential Skills task based assessments will indicate language progress. Expected CLB progress will be measured within the CLB 7/8 strands of reading and writing |
| May to August 2007 | Program promotion and student recruitment for second group of students | Project manager, ESL Instructor and Pharmacy Coordinator will promote program and recruit students | Referrals and inquiries lead to applications for second intake of students | Second group of up to 10 students to start second program cycle |
| August 07/ December 07/ April/08 August/08 Dec/08 | Remainder of Advisory Committee Meetings | Project staff and Advisory committee members will meet to review activities and evaluation ( program and learner progress) of program so far | We will learn what works and what doesn’t work in the first program needs to be changed, modified or refined about the first components from the first intake | Modifications will be made to program curriculum and model based on student, staff and advisory committee feedback |
| Sept/October 07 | Evaluation of Technical Exam Review prep component | Participants will be given two assessments: CLB task based assessment and a Content based assessment. Students and staff will do a program level evaluation. | Instructors and Participants will be able to measure their language level progress as well as technical knowledge | 60 to 70 % of Participants will be ready to write the Qualifying and/or Evaluating exams CLB task level assessment will show progress within the individual’s entrance CLB level |
| Aug to October 2007 | Arrange practicum placements for first class of students | Pharmacy Coordinator/Advocate will contact Pharmacy industry starting with those that Robertson has practicum contracts with and with Advisory committee to arrange practicum placements | Pharmacy Industry will respond favorably and cooperate to offer practicum placements | At least 70% of participants will be ready for a practicum and will have secured practicum placements in a timely manner. The remaining 30% will have placements within two to 5 months of their practicum component. |
| Mid September to mid December 2007 | First class- OSCE preparation - weekly 3 hour sessions – 3 month cycle- 36 hours | Pharmacy Educator and ESL instructor will work as a team to prepare students for OSCE exam using case studies and practice scenarios that will introduce participants to the Pharmaceutical Care competencies that are key to passing the OSCE exam. | Students will benefit from the expertise and skills of a content expert and a language expert while they practice the competencies in a hands on setting | Students will adopt the competencies and demonstrate skill and knowledge using them through a series of CLB/Essential skills task based assessments which will measure progress towards achievement of CLB 8 level of language competency |
| September 2007 | Second program cycle – 2nd class of students – Orientation and Resource workshops | Pharmacy Coordinator will facilitate the orientation workshops Participants will receive info and guidance on the initial application process. A check list of procedural and process requirements will be given to participants. Participants will receive individual counseling regarding their personal circumstances | Participants will become aware of what they individually need to do to prepare for the first qualifying exam and to be ready for the OSCE and practicum requirements | Participants will have all documents completed and in place to move forward in the application and certification process. Checklist will determine how prepared students are to go on to the next component in the program. |
| End of Sept 07 | Evaluation of Orientation and Resource Workshop component – 2nd class | An evaluation form will be distributed to all participants An evaluation form will be distributed to Staff. No language assessment will be necessary after the Orientation workshops as this component is informational and individual counseling is related to the process of the application. | Participants and staff will have an opportunity to evaluate the program up to this point | 100% of participants and staff will have filled out the evaluation forms. |
| October to December 2007 | Second Class - Technical Exam Review Component – Workshops, support groups, tutoring to prepare for the Qualifying Exam Part I (MCQ), Evaluation exam and OSCE - . (Weekly 3 hour sessions – 3 month cycle) | Technical Review material will be made available to students. Pharmacy Educator will conduct workshops on, technical content expected on the exams. ESL instructor will conduct study strategies, language strategies workshops to support participants in overcoming the English language obstacles. | Students will be ready to write the MCQ exam. English Reading and writing will have improved enough to be ready for success in the MCQ exam. | Technical mock tests will indicate the participants’ readiness level. CLB/Essential Skills task based assessments will indicate language progress. Expected CLB progress will be measured within the CLB 7/8 strands of reading and writing |
| End of December 2007 | Evaluation of Practicum Preparation Component – first class | Participants will be given two assessments: CLB task based assessment and a Content based assessment to determine their practicum hands on experience. Preceptor and Pharmacy Coordinator will assess participant’s progress based on the practicum checklist that student and preceptor were provided. Students and staff will do a program level evaluation. | Instructors and Participants will be able to measure their language level progress as well as technical knowledge. Student, preceptor and Pharmacy Coordinator will have evaluated level of readiness for OSCE exam. | 60 to 70 % of Participants will be ready to write the OSCE exam. CLB task level assessment will show progress within the individual’s entrance CLB level as well as level of NAPRA competency related to client pharmaceutical. |
| Jan/08 to March 08 | Arrange practicum placements for students in second class who will be needing them | Pharmacy Coordinator/Advocate will contact Pharmacy industry starting with those that Robertson has practicum contracts with and with Advisory committee to arrange practicum placements | Pharmacy Industry will respond favorably and cooperate to offer practicum placements | At least 70% of participants will be ready for a practicum and will have secured practicum placements in a timely manner. The remaining 30% will have placements within two to 5 months of their practicum component. |
| January 2008 to March 2008 | Second Class - OSCE preparation - weekly 3 hour sessions – 3 month cycle- 36 hours | Pharmacy Educator and ESL instructor will work as a team to prepare students for OSCE exam using case studies and practice scenarios that will introduce participants to the Pharmaceutical Care competencies that are key to passing the OSCE exam. | Students will benefit from the expertise and skills of a content expert and a language expert while they practice the competencies in a hands on setting | Students will adopt the competencies and demonstrate skill and knowledge using them through a series of CLB/Essential skills task based assessments which will measure progress towards achievement of CLB 8 level of language competency |
| March/April 2008 | Evaluation of OSCE Preparation Component –second class | Participants will be given two assessments: CLB task based assessment and a Content based assessment to determine their practicum hands on experience. Preceptor and Pharmacy Coordinator will assess participant’s progress based on the practicum checklist that student and preceptor were provided. Students and staff will do a program level evaluation. | Instructors and Participants will be able to measure their language level progress as well as technical knowledge. Student, preceptor and Pharmacy Coordinator will have evaluated level of readiness for OSCE exam. | 60 to 70 % of Participants will be ready to write the OSCE exam. CLB task level assessment will show progress within the individual’s entrance CLB level as well as level of NAPRA competency related to client pharmaceutical. |
| January 2008 – July 2008 | First class – Practicum preparation and placement ( Weekly 3 hour sessions – prior to practicum placement and during placement to coincide with 1,000 hour practicum placement requirement – 7 months) | Participants will be placed in a 2 week job shadow prior to permanent practicum placement Job shadow will be 2 part time shifts a week and one 3 hour weekly class to debrief the experience prior to practicum placement Practicum placement will be supplemented by a 3 hour a week workshop to review, discuss and prepare for ongoing practicum requirements. | Students will have insight into what to expect during a fulltime practicum. Students will have support and opportunities weekly to debrief and prepare weekly for practicum expectations. placement | At least 60% of students will be ready to complete certification process by end of practicum cycle. The remaining 40% will be ready within one year of completing program. |
| April 2008 | End of term evaluation of Practicum Preparation component of first class who are out on practicum | A practicum competency checklist will be provided to the Preceptor and the learner and will be used to assess against NAPRA competencies and readiness for final certification (OSCE exam) A program level evaluation will be administered to staff and students. | Staff and students will learn what worked and what didn’t work .Modifications/changes will be made for next class. | CLB exit level of 60% who are ready for certification will be 8/9 |
| April 2008 – October 2008 | Second class – Practicum preparation Weekly 3 hour sessions – prior to practicum placement and during placement to coincide with 1,000 hour practicum placement requirement – 7 months) | Participants will be placed in a 2 week job shadow prior to permanent practicum placement Job shadow will be 2 part time shifts a week and one 3 hour weekly class to debrief the experience prior to practicum placement Practicum placement will be supplemented by a 3 hour a week workshop to review, discuss and prepare for ongoing practicum requirements. | Students will have insight into what to expect during a fulltime practicum. Students will have support and opportunities weekly to debrief and prepare weekly for practicum expectations. placement | At least 60% of students will be ready to complete certification process by end of practicum cycle. The remaining 40% will be ready within one year of completing program. |
| July 08 | End of term evaluation of Practicum Preparation component of second class who are out on practicum | A practicum competency checklist will be provided to the Preceptor and the learner and will be used to assess against NAPRA competencies and readiness for final certification (OSCE exam) A program level evaluation will be administered to staff and students. | Staff and students will learn what worked and what didn’t work .Modifications/changes will be made for next class. | CLB exit level of 60% who are ready for certification will be 8/9 At least 60% of students will be ready to complete certification process by end of practicum cycle. |
| Nov – Dec 08 | Data Gathering and preparation of final report | Collection of all data from applications, evaluations, assessments will be collected and compiled by Project team | Pharmacy Coordinator and Project Manager will prepare final report | Results of two groups of students will show that this program model was effective. 60 to 70% of participants will have been certified and will have found employment as a Pharmacist. CLB levels of 60 to 70% of participants will have progressed to CLB8/9 |

Refer to Appendix #4 for timelines spreadsheet..

Project Costs

| Contributions of your organization and partner organizations |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Category | Contributor | Letter of Support attached | Financial | In-kind | Total Contribution of Partners |
|  | Advisory Committee Members : | yes |  |  |  |
| Time/expertise | Mayuri Modgill Pharmacist |  |  | 3hrs x7 meetings x $75/hr - $700 = $875.00 | 875.00 |
| Time/expertise | Amgad Zakhari Pharmacist |  |  | 3hrs x7 meetings x $75/hr - $700 = $875.00 | 875.00 |
| Time/expertise | Lana Mallikhina Pharmacist |  |  | 3hrs x7 meetings x $75/hr - $700 = $875.00 | 875.00 |
| Time/expertise | Trent Lane Regional Pharmacy Manager Canada Safeway |  |  | 3hrs x7 meetings x $75/hr - $700 = $875.00 | 875.00 |
| Time/expertise | Audrey Flegel Pharmacy Manager Coop Stores |  |  | 3hrs x7 meetings x $75/hr - $700 = $875.00 | 875.00 |
| Time/expertise | Amyn Kanji Pharmacist/Owner |  |  | 3hrs x7 meetings x $75/hr - $700 = $875.00 | 875.00 |
| Portion of admin costs for postage, supplies, Audit fees, bank fees, supplies. | Robertson College |  |  | Portion of admin costs for postage, supplies, Audit fees, bank fees, supplies - $300.00 Admin support (5hrs/wkx$15/hrx24mths x4 wks = $7,200.00 | 7,500.00 |
| Total contributions from all partners |  |  | $ | $ | $12,750.00 |

Total Budget

| Administrative (examples below) |  |  | $ Amount |  |
| --- | --- | --- | --- | --- |
| QTY | Job Title or Item Description. All Administrative Positions (e.g. Executive Director, Project Co-ordinator etc.) | Details (e.g. $/hr x #hrs x #wks, $/mths x #mths) |  |  |
| 1 | Director/Project Manager | 5 hrs /week x 24mths x 4 wks x$60/hr. | 28,800.00 |  |
| 1 | Pharmacy Coordinator/Advocate | 15/hrs/wk x 24mths x 4wks x$60/hr | 86,400.00 |  |
|  | Office space rental | 3 office spaces x 500/mthx 24mth | 36,000.00 |  |
|  | Utilities |  |  |  |
|  | Materials and supplies | $!00/mthx24mths (balance Robertson in kind) | 2,400.00 |  |
|  | Computer software |  |  |  |
|  | Staff travel | Included in Program Delivery costs |  |  |
|  | Audit Fee | Robertson In kind |  |  |
|  | Bank Charges |  |  |  |
|  | Postage | $50/mthx 24mths | $1,200.00 |  |
|  | Insurance, Permits, Licenses etc. | Robertson In kind |  |  |
|  | Telephone, Fax, Internet | Included in Program Delivery |  |  |
|  | Benefits (MERC) specify here | 15% of admin wages | 17,280.00 |  |
| Total Administrative |  |  | $172,080.00 |  |
| Program Delivery |  |  | $ Amount |  |
| Qty | Job Title or Item Description. All staff (e.g. ESL Instructors, Employment Outreach Co-ordinator etc.) | Details (e.g. $/hr x #hrs x #wks, $/mths x #mths) |  |  |
| 1 | Pharmacy Educator | 6hrs/wkx24mthsx 4wks x $60/hr + 3hrs/wk prep timex24mthsx $60 | 51,840.00 |  |
| 1 | ESL Instructor | 6hrs/wkx24mthsx 4wks x $50/hr + 3hrs/wk prep timex24mthsx $50 | 43,200.00 |  |
| 5 | Advisory Committee Members | 7 meetings x $100 x up to 8 members (honoraria) | 5600.00 |  |
| 1 | Pharmacy Educator | 6hrs/wk x 24mthsx 4wks x $60/hr + 3hrs/wk prep timex24mthsx $60 | 51,840.00 |  |
|  | Classroom Rental | Pharmacy Lab and 2classrooms x 2 times/wk x $1,000/mthx 20mths | 20,000.00 |  |
|  | Class Materials and Supplies | $1,000 x30 students | 30,000.00 |  |
|  | Photocopying | $50/mth x 30 students x 14mths | 21,000 |  |
|  | Telephone, fax and internet | $100/mth x24mths | 2,400.00 |  |
|  | Computer software |  |  |  |
|  | Utilities |  |  |  |
|  | Postage |  |  |  |
|  | Travel | Travel to Edmonton to ACP offices x 2 x 3people x $300 | 1,800.00 |  |
|  | Professional Development | Training – 4wksx6 hrsx1x50+1x60 | 2,640.00 |  |
|  | Benefits (MERC) specify here | 15% of staff wages | 22,428.00 |  |
| Total Program Delivery |  |  | $252,748.00 |  |
| Total Capital |  |  | $ Amount |  |
| Qty | Item Description | Details |  |  |
|  | NA |  |  |  |
| Total Capital. | NA. |  |
| Other |  |  | $ Amount |  |
|  | Indicate living allowance requirements | How many learners at $1000 per month | NA |  |
| Total Other |  |  |  |  |
| Total Eligible GST/HST: GST/HST paid on purchases less input tax credit/rebate: |  |  |  |  |
| Grand Total |  |  | $424,828.00 |  |

Your Declaration:

As an official with signing authority for the applying organization, I declare that the given information is accurate and complete and the application is being made by the organization named.

Name (printed) ______________

Position _________________________

Signature: _________________________

Date: ____________________

Apprendix # 1 - Practicum Sites and Employers

- Shoppers Drug Mart (various locations throughout Alberta)

- Super Drug Mart (various locations throughout Alberta)

- Rexall Pharmacy (various locations throughout the city)

- Calgary Co-op (various locations throughout the city)

- Canada Safeway (various locations throughout Alberta)

- Pharmacy Plus

- Calea

- Minute Drugs

- Medicine Shoppe Pharmacy (various locations throughout the city)

- Kenron Pharmacy

- Pharmacy on Call

- Zellers Pharmacy

- Rexall Managed Care Pharmacy

- Medisystems Pharmacy (formerly Central Care Pharmacy)

- Drugstore Pharmacy (various locations throughout Alberta and British Columbia)

- Belleville General Hospital (Belleville, ON)

- Deer Lodge (Winnipeg, MN)

- Cross Cancer Institute Edmonton

- Alberta Hospital Ponoka

- Hanna Health Centre

- Lethbridge Regional Hospital

- St. Michael’s Health Centre Lethbridge

- Queen Elizabeth II Hospital Grande Prairie

- Blue Quill Pharmacy Edmonton

- Mineral Springs Hospital Banff

- High River Hospital

- Oilfields Hospital Black Diamond

- St. Joseph’s Hospital (Vancouver Island)

- Cumberland Lodge (Vancouver Island)

- IDA Pharmacy (various locations throughout the city)

- Peter Lougheed Centre

- Foothills Medical Centre

- Holy Cross Medical Centre Pharmacy

- Alberta Clinic Pharmacy

- Outpatients Pharmacy Services (CHR)

- Alberta Children’s Hospital

- Central Production Pharmacy

- Rockyview Hospital

- Tom Baker Cancer Centre

- Total Care Pharmacy

- Carewest – Fanning Centre

- Intercare

- We Care

- Bethany Society

- Father Lacombe Centre

- Brenda Strafford Foundation

- Sharp Foundation

- Classic Care

- CHR Home Care

Appendix#2 - Sample Curriculum Planning Documents

ROBERTSON COLLEGE – COURSE and MODULE PLANNING TEMPLATE

(Adapted from templates included in Canadian Language Benchmarks 2000 Guide to Implementation)

| Program: |  | Course: |  |  | Level: |  |  | Module: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Goals: |  |  |  |  | Objectives: |  |  |  |
| EXPECTED OUTCOMES |  |  |  |  |  |  |  |  |
| CLB Language Competencies: |  |  | Essential Skills Competencies: |  |  | Content/Knowledge: |  |  |
| DELIVERY STRATEGIES |  |  |  |  |  |  |  |  |
| Instructional Strategies: |  | Activities: |  |  |  |  |  |  |
| ASSESSMENT STRATEGIES |  |  |  |  |  |  | Resources: |  |
| Canadian Language Benchmarks: | Essential Skills: |  |  | Content/Knowledge: |  |  |  |  |

ROBERTSON COLLEGE – LESSON/UNIT PLAN TEMPLATE

Adapted from templates included in Canadian Language Benchmarks 2000 Guide to Implementation)

| Course: | Level: |  | Module: |  | Unit: |  | Time Frame: |
| --- | --- | --- | --- | --- | --- | --- | --- |
| EXPECTED OUTCOMES |  |  |  |  |  |  |  |
| CLB Competencies |  | Essential Skills |  | Content/Knowledge |  | Industry Specific Competencies/Skills |  |
| DELIVERY PLAN – INTSTRUCTIONAL ACTIVITIES |  |  |  |  |  |  |  |
| CLB Competencies |  | Essential Skills |  | Content/Knowledge |  | Industry Specific Competencies/Skills |  |
| INSTRUCTIONAL AND LEARNING STRATEGIES |  |  |  |  |  |  |  |
| CLB Competencies |  | Essential Skills |  | Content/Knowledge |  | Industry Specific Competencies/Skills |  |
| ASSESSMENT PLAN |  |  |  |  |  |  |  |
| CLB Competencies |  | Essential Skills |  | Content/Knowledge |  | Industry Specific Competencies/Skills |  |
| RESOURCES/REFERENCES |  |  |  |  |  |  |  |
| CLB Competencies |  | Essential Skills |  | Content/Knowledge |  | Industry Specific Competencies/Skills |  |

Appendix # 3 - Project Staff Job Descriptions

Roles and Responsibilities of Staff Involved In the Project:

- Project Manager:

Qualifications and Experience:

- Project management experience

- ESL teaching and administrative experience (ATESL or TESL certification)

- Curriculum and program development experience

- Expertise and working knowledge of CLBs, Essential Skills, Integrated Skills training and NAPRA competencies

- Understanding of labour market as related to skilled immigrants and foreign trained professionals

Role and responsibilities:

- Oversee and manage all aspects of  the project

- prepare/submit final report

- Pharmacy Coordinator:

Qualifications and experience:

- Pharmacist who is registered to practice and has knowledge and partnerships within the Pharmacy Community

- At least 5 years of pharmacy practice in a retail setting

- Understands the Pharmacy application/certification process in order to take on the role of Pharmacist Advocate.

Role and Responsibilities:

- Will coordinate and liaise with the pharmacy community.

- Will assist students with practicum placement

- Assist in data collection and final report

- ESL Instructor:

Qualifications and experience:

- ATESL or TESL accreditation

- Minimum of a Bachelor's degree with a minimum of 250 contact hours of post-graduate or upper-level undergraduate coursework that focuses on specialized training in second-language teaching from provincially recognized post secondary institutions. The coursework must be recognized by a university as equivalent to senior level undergraduate coursework.

- At least 3 years of  ESL classroom teaching experience

- Experience in curriculum development of English for Special Purposes, English in the Workplace programs, knowledge of Essential Skills and Canadian Language Benchmarks

Role and Responsibilities:

- Develop lesson plans for each program component based on Pharmacy Preparation  Program curriculum

- Instruct language and cultural components of the curriculum based on CLB, Essential Skills and NAPRA competencies

- Assess language competency and progression based on CLB/Essential Skills Framework as related to NAPRA competencies

- Collaborate and team teach with Pharmacy Educator on lesson plan preparation to ensure that language and cultural components reflect the NAPRA competencies

- Collect data and prepare to contribute to final report.

- Pharmacy Educator(s):

Qualifications and Experience:

- Pharmacist who is registered to practice and has knowledge and partnerships within the Pharmacy Community

- At least 5 years of pharmacy practice in a retail setting

- Understands the Pharmacy application/certification process in order to take on the role of Pharmacist Advocate.

Role and Responsibilities:

- Pharmacist(s) will teach the technical and skills based curriculum components and will work with ESL Instructor to add context to language and cultural competency components of the curriculum.

- Evaluate and assess participants’ competency level after each program component based on NAPRA competencies in collaboration with ESL instructor

- Collect data and prepare to contribute to final report.

- Advisory Committee Members:

Qualifications and Experience:

- Advisory Committee made up of a member from the Alberta College of Pharmacists, Pharmacists from the retail and hospital areas. We have three Pharmacists on the current Robertson College Pharmacy Technician advisory committee who have offered to join this committee for consultation and advice.

- Members from Immigrant Serving Agencies such as CIWA(Calgary Immigrant Women’s Association), ECCC (Ethno Cultural Community Centre) and CCCSA (Calgary Chinese Community Services Association) who are supportive of developing this program initiative and will be represented on the Advisory Committee

Role and Responsibilities:

- The Advisory Committee will serve to make recommendations and provide guidance in delivering our program and curriculum material as well as best practices in the Pharmacy profession that will assist us in developing a program that will support the success of foreign trained pharmacists to pass the certification exams.

- The Advisory Committee will not be a working board, but a board that provides advice and guidance. As such, there will be no legal obligations on the part of the members. An honorarium will be given to acknowledge participation in each meeting.

- The advisory committee will meet approximately 6 times throughout the 2 year project or as needed.

Appendix # 4 – Timelines Spreadsheet

Appendix # 5 - Background Information

600, 900 6 AVE. SW. CALGARY, AB T2P 3K2 (403) 920-0070

www. RobertsonCollege.com Calgary@RobertsonCollege.com

Robertson College is a vocational/career college with campuses worldwide. We offer a wide range of practical and theoretical programs designed to meet the needs of students and employers alike in today's rapidly changing business environment.

A World Leader in Private Education

Robertson College started in Saskatchewan as a Secretarial School and evolved into a Career / Vocational College with campuses in:

- Winnipeg

- Brandon

- Calgary

- China

Each of these locations are dedicated to providing students with a practical, focused education designed to give students the skills they need to enter into the workforce within one year. All of our locations are staffed by Canadian instructors and use approved Canadian curriculum.

Our Goal

Our goal is to provide our students with the essential skills that will enable them to secure rewarding, fulfilling careers in their chosen field.

Mission Statement

To assist students in realizing their career goals within 3 months of graduation through attendance in a prestigious vocational college and through meaningful practicum assignments.

Personalized Instruction

Small class sizes (each less than 15 students) mean faculty and students develop strong relationships. Robertson instructors are professionals in their field and bring the required expertise and experience to our programs.

Robertson College Programs

We offer a wide range of practical and theoretical programs designed to meet the needs of students and employers alike in today's rapidly changing business environment:

Health Care Department:

- Pharmacy Technician Retail/Institutional)

- Government of Alberta Health Care Aide

- Vet Office Assistant

Business and Human Relations Department:

- Travel Counsellor

- International Hospitality and Hotel Management

- Administrative Office Professional

- Legal Office Assistant

- Life Skills Educator Training (pending licensing)

ESL Department (Calgary):

- ESENCE

- Maple Health Care Aide

- Maple Pharmacy Technician

- Pharmacy Prep for Foreign Trained Pharmacists (under development)

Other programs in Winnipeg and Brandon Manitoba:

- Medical Office Assistant

- Accounting and Payroll

- Health Unit Clerk

- Admin Professional/Accounting

- Network Engineering Professional

- Radio Broadcasting

China:

- Live In Care Giver Program

Appendix #6 – Letter of Support

Appendix # 7 - Robertson College Organizational Chart

Director – Winnipeg Campus

President/CEO –

Ken Penner

IT Department Head - Winnipeg

Director – Calgary Campus

Vice Principal Academic

Business Program Instructors

ESL Program Department Head

Brandon Campus Director

Health Program

Instructors

China – Live In Care Giver Program

Student Services

Student Services

Health and Business Instructors

Admin Assistant

IT Instructors/

LIC Instructors

ESL Project Coordinators/

Instructors

Vocational Instructors

Administrative Assistant

Administrative Assistant

Student Services

Student Services

Vocational Program Department Head

Helen Penner – Owner. (No Board of Directors)

Approximately 75 staff in total.

Appendix #8- Certificate of Incorporation

Appendix #9 – Most Recent Financial Statement

Appendix #10 – Insurance Certificate
Appendix #11 - Declaration

As an official with signing authority for the applying organization, I declare that the given information is accurate and complete and the application is being made by the organization named.

Name (printed) __Maria MacMinn____________

Position _____Director, Calgary Campus_____

Signature: _________________________

Date: ____________________

Data source: 2003 Wage and Salary Survey (www.alis.gov.ab.ca/wage/info) ; Alberta Labour Market Outlook 2005

Health Canada News Release, April 2005